## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | PREDICTION OF MOTOR VEHICLE BRAKE PAD
PROJECT MANAGER | MUHAMMAD ADAM HAFIZI BIN HASHIM TEE
COMPANY NAME | ABS BREAK SDN BHD
DATE | 2023-10-01 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Initiation
1.1 | Identify Problem Statement | Adam | 2023-10-02 | 2023-10-06 | 4 | 100%
1.2 | Identify Project Scope | Adam | 2023-10-05 | 2023-10-10 | 5 | 100%
1.3 | Identify Project Deliverables | Farihah | 2023-10-10 | 2023-10-13 | 3 | 100%
1.4 | Identify Project Stakeholders | Farihah | 2023-10-12 | 2023-10-17 | 5 | 100%
1.5 | Develop a Business Case | Nawal | 2023-10-13 | 2023-10-18 | 5 | 100%
1.6 | Develop Project Initiation Document | Amir | 2023-10-18 | 2023-10-20 | 2 | 100%
2 | Planning
2.1 | Project Timeline | Farihah | 2023-10-23 | 2023-10-25 | 2 | 100%
2.2 | Workflow Documents | Farihah | 2023-10-24 | 2023-10-26 | 2 | 100%
2.3 | Budget Planning | Nawal | 2023-10-26 | 2023-10-31 | 5 | 100%
2.4 | Gathering Resources | Amir | 2023-10-30 | 2023-11-08 | 9 | 100%
2.5 | Identify Project Risk | Amir | 2023-11-06 | 2023-11-10 | 4 | 100%
3 | Execution
3.1 | Identify Project Task and Workflows | Farihah | 2023-11-13 | 2023-11-15 | 2 | 100%
3.2 | Assigning Task For Each Team Member | Adam | 2023-11-15 | 2023-11-17 | 2 | 100%
3.3 | Updating Progress Of Each Team Member | Farihah | 2023-11-17 | 2023-12-01 | 14 | 20%
3.4 | Updating Stakeholders | Adam | 2023-11-17 | 2023-12-01 | 14 | 10%
3.5 | Quality Of Work Monitoring | Adam | 2023-11-17 | 2023-12-01 | 14 | 10%
3.6 | Managing Budget | Nawal | 2023-11-30 | 2023-12-01 | 1 | 20%
4 | Closure
4.1 | Fulfillment Of Project Goals | Adam | 2023-12-04 | 2023-12-07 | 3 | 0%
4.2 | Initial Problem Solve | Amir | 2023-12-06 | 2023-12-11 | 5 | 0%
4.3 | Team Member Evaluation | Amir | 2023-12-12 | 2023-12-14 | 2 | 0%
4.4 | Project Manager Evaluation | Adam | 2023-12-15 | 2023-12-19 | 4 | 0%
4.5 | Stakeholders Report | Farihah | 2023-12-04 | 2023-12-08 | 4 | 0%
4.6 | Project Final Analysis Report | Amir | 2023-12-14 | 2023-12-21 | 7 | 0%
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])